## Final
[7 empty] | Sophie | 1400 | Alistair | 1560 | Darcy | 1400
Milestone | Objective | Reporting requirement | Reporting requirement | Milestone description | Due date | Fixed price | Days | $$ | Days | $$ | Days | $$
1 | 1 | 1 | 1 | Update standard and implement categorical modelling approaches to estimate scaled length and age frequencies | 2022-06-30 | 30520 | 2 | 2800 | 7 | 10920 | 12 | 16800
2 | 1 | 1 | 1 | Evaluate, via simulation, the relative accuracy and effectiveness of different methods | 2022-06-30 | 13940 | 0.5 | 700 | 4 | 6240 | 5 | 7000
3 | 2 | 1 | 1 | Apply the methods to case study examples (e.g., Chatham Rise & sub-Antarctic ling, and west coast South Island and sub-Antarctic hake) and compare the outcomes on the resulting length and age-frequencies | 2022-06-30 | 6540 | 1 | 1400 | 1.5 | 2340 | 2 | 2800
4 | 3 | 1 | 1 | Submit a draft FAR (as per Reporting Form 6) to MPI | 2022-06-30 | 5840 | 0.5 | 700 | 1.5 | 2340 | 2 | 2800
5 | 3 | 1 | 2 | Present methods and results to the FNZ Statistics, Assessments, and Methods Working Group (SAMWG) | 2022-10-30 | 3660 | 0.5 | 700 | 1 | 1560 | 1 | 1400
6 | 3 | 1 | 3 | Submit a final FAR (as per Reporting Form 6) to MPI | 2022-10-30 | 2180 | 0.5 | 700 | 0.5 | 780 | 0.5 | 700
7 | 3 |  | 4 | Submit data to the Fisheries New Zealand data management team | 2022-12-16 | 3270 | 0.75 | 1050 | 0.75 | 1170 | 0.75 | 1050
| TOTAL |  |  |  |  | 65950 | 5.75 | 8050 | 16.25 | 25350 | 23.25 | 32550
[5 empty] | Data percentage | 4.958%

## Proposal
[6 empty] | Sophie | 1400 | Alistair | 1560 | Darcy | 1400 | Adam? | 1400
Milestone | Objective | Reporting requirement | Milestone description | Due date | Fixed price | Days | $$ | Days | $$ | Days | $$ | Days | $$
1 | 1 | 1 | Complete initial engagement with FNZ on project | 2021-11-30 | 1286 | 0.125 | 175 | 0.6 | 936 | 0.125 | 175 | 0 | 0
2 | 1 | 1 | Extract & groom data and complete the fisheries characterisation | 2022-02-28 | 8500 | 0.5 | 700 | 5 | 7800 | 0 | 0 | 0 | 0
3 | 1 | 1 | Undertake the spatial temporal-modelling | 2022-02-28 | 9040 | 0 | 0 | 4 | 6240 | 2 | 2800 | 0 | 0
4 | 1 | 1 | Complete CPUE analyses | 2022-02-28 | 10384 | 0.4 | 560 | 5.4 | 8424 | 0 | 0 | 1 | 1400
5 | 1 | 1 | Present the characterisation, CPUE indices and any other relevant analyses to the Deepwater Fisheries Assessment Working Group | 2022-02-28 | 1560 | 0 | 0 | 1 | 1560 | 0 | 0 | 0 | 0
|  |  | Sub-total (invoice INV-00xx) |  | 30770 | 1.025 | 1435 | 16 | 24960 | 2.125 | 2975 | 1 | 1400
6 | 2 | 1 | Complete the CASAL assessment modelling | 2022-04-30 | 29480 | 1 | 1400 | 18 | 28080 | 0 | 0 | 0 | 0
7 | 2 | 1 | Present the assessment results and any other relevant analyses to the Deepwater Fisheries Assessment Working Group | 2022-04-30 | 2960 | 0.5 | 700 | 1 | 1560 | 0.5 | 700 | 0 | 0
|  |  | Sub-total (invoice INV-00xx) |  | 32440 | 1.5 | 2100 | 19 | 29640 | 0.5 | 700 | 0 | 0
8 | 1 & 2 | 2 | Submit a draft revised Working Group Report to the Ministry for Primary Industries | 2022-04-30 | 1092 | 0 | 0 | 0.7 | 1092 | 0 | 0 | 0 | 0
9 | 1 & 2 | 3 | Submit Fisheries Assessment Report to the Ministry for Primary Industries. Milestone payment on approval of FAR by MPI; provide relevant stock assessment inputs and outputs to the RAM Legacy database project | 2022-08-31 | 10480 | 0.3 | 420 | 6 | 9360 | 0.5 | 700 | 0 | 0
10 | 1 & 2 | 4 | Submit data and code through the Research Data Manager as per Data Management Plan | 2022-08-31 | 1060 | 0.2 | 280 | 0.5 | 780 | 0 | 0 | 0 | 0
11 | Final | 4 | Acceptance of submitted data through the Research Data Manager as per Data Management Plan. | 2022-09-30 | 4075 | 0 | 0 | 2.5 | 3900 | 0.125 | 175 | 0 | 0
|  |  | Sub-total (invoice INV-00xx) |  | 16707 | 0.5 | 700 | 9.7 | 15132 | 0.625 | 875 | 0 | 0
| TOTAL |  |  |  | 79917 | 3.025 | 4235 | 44.7 | 69732 | 3.25 | 4550 | 1 | 1400
EXCEPTIONS AND DEVIATIONS
12 | 1 | 1 | MS1: Revise length-weight and growth parameters | 28/02/202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 2 | 1 | MS2: Age ratio-logit GAMs | 2022-06-30 | 22600 | 0.5 | 700 | 10 | 15600 | 4.5 | 6300 | 0 | 0
14 | 2 | 1 | MS2: Complete Stan modelling | 2022-04-30 | 26920 | 1 | 1400 | 2 | 3120 | 16 | 22400 | 0 | 0
[5 empty] | MS1 % | 38.5%
[5 empty] | MS2 % | 61.5%
|  |  | FNZ BUDGET | 75000 | -4917
|  |  | FNZ BUDGET + 10% | 82500 | 2583
|  |  |  | Percent data submission | 5.099 | %